## Cronograma de trabalho
Atividades | Período de Execução em Meses
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Gestão da missão de sanduíche
Reunião inicial com orientador estrangeiro | n
Reuniões de acompanhamento com orientador brasileiro e estrangeiro |  | n | n | n | n | n | n | n | n | n | n
Semiários de pesquisa
Estruturação das ações finais do projeto
Reunião de avaliação final da bolsa | [11 empty] | n
Pesquisa
xxx
xxx
xxx
xxx
xxx
xxx

## Novo
Activities | Period of execution in months
[10 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020
| 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3
Academic training
Planning meeting | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n
Follow-up meeting |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n
Research seminar |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n
Elaboration of scientific articles |  | n | n |  | n | n |  | n | n |  |  |  |  | n | n |  | n | n |  | n | n |  |  |  |  | n | n |  | n | n |  | n | n |  |  |  |  | n | n |  | n | n |  | n | n
Evaluation meeting |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n
Elaboration of the research proposal | [17 empty] | n | n
Project presentation | [19 empty] | n
Writing preliminary results | [20 empty] | n | n | n | n | n | n | n | n | n
Pre-defense of the thesis | [31 empty] | n
Teaching Internship | [30 empty] | n | n | n
Thesis writing | [33 empty] | n | n | n | n | n | n | n | n | n | n | n | n
Thesis defense | [47 empty] | n
Research

## Novo (2)
Atividades | Período de Execução em Meses
2016
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Reunião de planejamento | n | n | n | n | n | n | n | n | n | n | n
Reunião de acompanhamento | n | n | n | n | n | n | n | n | n | n | n
Seminário de pesquisa |  |  |  |  | n |  |  | n |  |  | n
Elaboração de artigo científico |  |  |  |  | n |  |  | n |  |  | n
Reunião de avaliação | [11 empty] | n
Pesquisa
Definição de critérios objetivos para seleção das plataformas de integração a serem estudadas | n
Estudo do motor de cada plataforma selecionada | n | n | n
Identificação das funcionalidades que possam ter um impacto no desempenho dos motores |  |  | n
Desenvolvimento de um framework de comparação para motores de integração |  |  | n | n
Aplicação do framework desenvolvido para comparar as plataformas selecionadas |  |  |  | n
Identificação das fragilidades dos motores de execução atuais |  |  |  | n
Elaboração de relatório técnico parcial |  |  |  |  | n
Elaboração de proposta de um novo modelo para motor de execução mais eficiente que os atuais | [5 empty] | n | n | n
Desenvolvimento de prova de conceito para medir os ganhos do novo motor proposto | [7 empty] | n | n | n | n
Seleção de um conjunto de datasets para demonstrar o funcionamento do novo motor proposto | [9 empty] | n | n
Elaboração de relatório técnico final da bolsa | [11 empty] | n

## Novo (3)
Activities | Period of execution in months
| 2016 | [8 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020
| 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3
General
Planning meeting | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n
Follow-up meeting |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n
Research seminar |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n
Elaboration of scientific articles | [5 empty] | n |  | n | n |  |  |  |  | n | n |  | n | n |  | n | n |  |  |  |  | n | n |  | n | n |  | n | n |  |  |  |  | n | n |  | n | n |  | n | n
Evaluation meeting |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n |  |  | n
Elaboration of the research proposal | [17 empty] | n | n
Project presentation | [19 empty] | n
Writing preliminary results | [20 empty] | n | n | n | n | n | n | n | n | n | n
Pre-defense of the thesis | [31 empty] | n
Teaching Internship | [30 empty] | n | n | n
Thesis defense and writing | [39 empty] | n | n | n | n | n | n | n | n | n
Research
Literature review | n | n | n | n | n | n | n | n | n
Definition of objective criteria for selecting a set of integration platforms to be studied | [5 empty] | n | n | n | n
Study of the runtime system of each selected platform | [9 empty] | n | n
Identification of properties that may have an impact on the performance of runtime systems | [9 empty] | n | n | n | n
Development of a comparison framework for integration runtime system | [11 empty] | n | n | n | n
Framework application developed to compare selected platforms | [15 empty] | n | n
Identification of the weaknesses of the runtime systems of the integration platforms studied | [9 empty] | n | n | n | n | n | n | n | n | n | n
Elaboration of proposal of a new model for a runtime system more efficient | [21 empty] | n | n | n | n | n | n
Sandwich doctorate | [23 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n
Proof of concept development to measure the gains of the proposed runtime system | [27 empty] | n | n | n | n | n | n
Selection of a set of datasets to demonstrate the operation of the proposed runtime system | [33 empty] | n | n | n
Validation | [36 empty] | n | n | n